DEPA CAMP

Project:  Autonomous Robot

Project 1: Autonomous Suite (Team builds one robot that can)

- Follow a black line reliably (line following).

- Run automatically to reach a destination (map navigation).

- Racing (timed sprint).

Project 2: Robot football

Hardware per team (single robot)

  1 × ESP32 development board (ESP32-WROOM or similar)

  1 × Motor driver (L298N OR preferred: TB6612 or dual H-bridge supporting 4 motors)

  4 × DC geared motors with encoders (or at least 2 with encoders if cost is tight) — for stable speed & odometry. (If encoders unavailable, you can use timed motor commands + landmarks.)

  1 × 4-wheel chassis + mounting hardware and caster wheel

  4 × motor wheels

  1 × IR line sensor array (3 or 5 sensors) or 5 × QRE1113/IR reflectance sensors + breakout board

  1 × IMU (MPU-6050 / MPU-9250) — optional but helpful for odometry/pose correction

  2 × ultrasonic sensors (HC-SR04) or short-range LIDAR (optional) — for obstacle detection in football mode

  1 × battery pack (7.4–11.1V LiPo or 6×AA + voltage regulator) and charging module

  1 × 5V regulator (if not onboard)

  Jumper wires, breadboard / small PCB for wiring, screws, zip ties

  Optional: small push buttons / LEDs for mode selection and status

# Software & tools (per team)

- Arduino IDE or PlatformIO configured for ESP32

- Motor/pwm libraries (or direct use of ledc on ESP32)

- Wi-Fi WebSocket / WebServer or Bluetooth Serial for teleop

- Optional: a simple phone web UI (HTML/JS) to send commands

Tasks 1:   Map made of lines + marked intersection

Task 2: Method B — Odometry + IMU waypoints
Task 3: Speed run (which robot is fastest)

Task 4: Robot football

Day 1:  Assembly + Basic firmware  – Wednesday 12.11

Goal: chassis built, motors wired, ESP32 boots, motor control & sensors read.

- 09:30–11:00 — Kickoff & safety briefing, distribute roles & kit (all), Mechanical assembly & motor mounting . (1.5 h each)

- 11:00–12:30 — Electronics wiring: motor driver, power, sensors, button/LED. (1.5 h each)

- 12:30–13:00 — Lunch

- 13:00–15:00 — Firmware skeleton: blink, motor PWM, reading encoder interrupts, IR sensor raw reads. (2 h each)

- 15:00–16:00 — Motor tuning & simple open-loop forward/back test; integrate PWM + direction. (1 h total)

- 16:00–17:00 — Integration test: move forward, stop, read sensors, repo commit & demo (all). (1 h all)

Milestones to check by end of Day1:

- Robot moves forward/backwards reliably.

- IR sensors give stable readings.

- ESP32 code deploys via USB.

- Battery powering safely.

Day 2: Line following + map navigation (9 hours)

Goal: Implement stable line following and basic map navigation demo.

- 09:30–11:30 — Quick review, split tasks (all), Implement line following PID and tune parameters on the track. (2 h)

- 11:30–12:30 — Test & iterate; students rotate driving & observing (all). (1 h)

- 12:30–13:00 — Lunch

- 13:00–15:00 — Intersection detection & state machine for map navigation. Add simple turn execution routines . (2 h)

- 15:00–16:30 — Integrate waypoint markers (colored stickers) and decide logic to select turn. (D + E). (1.5 h)

- 16:30–17:30 — Full autonomous run demo (tune), document method, run multiple trials (all). (1 h)

Milestones End of Day2:

- Robot can follow line at walking speed reliably (≥3/5 successful runs).

- Robot can navigate predefined map to a destination using markers or intersections.

Day 3: Speed run, football mode, testing & demonstration (9 hours)

Goal: Finalize speed run and build teleop football mode. Prepare final demo & report.

- 09:30–11:00 — Plan for day, safety check (all), Speed run mode: enable open throttle, measure speed (encoders/time), and tune motor driver.. (1.5 h)

- 11:00–12:30 — Implement Wi-Fi/Bluetooth teleop and simple mobile UI. (1.5 h)

- 12:30–13:00 — Lunch

- 13:00–15:30 — Teleop testing and robot football practice (all). (2.5 h)

- 15:30–16:30 — Final debugging and demonstrations for instructors (all). (1 h)

- 16:30–17:30 — Grading demo: run line/auto map/speed + 3-minute teleop match, final report & code push (all). (1 h)

Milestones End of Day3:

- Completed demos for all four tasks.

- Working teleop UI and match performed.

- Code pushed & short demo report submitted.

Continuation, Day 4-5 / Telemetry implementation & data collection.

Objective

Students extend their robots with sensors, collect real telemetry data during robot operation, and send it through the prepared MQTT-MongoDB data pipeline for storage and basic analysis.

### Day 4 – Integrating Telemetry and Publishing to Cloud

Goal: Equip the robot with sensors and send live data through the MQTT bridge to MongoDB.

• 09:30–10:00 — Introduction to IoT data flow: explain ESP32 → MQTT → Bridge → MongoDB, review network credentials. (0.5 h)
• 10:00–11:00 — Set up Arduino IDE with ArduinoJSON, PubSubClient, and sensor libraries (Adafruit ADXL345 / DHT). (1 h)
• 11:00–12:30 — Mount and wire sensors (ADXL345 or DHT11) to ESP32 and verify readings in Serial Monitor. (1.5 h)
• 12:30–13:00 — Lunch
• 13:00–15:00 — Integrate telemetry with MQTT publisher code; send JSON data to team topic on broker. (2 h)
• 15:00–16:00 — Verify data flow on Shiftr.io dashboard and confirm entries in MongoDB workshop_teamXX collection. (1 h)
• 16:00–17:00 — Telemetry testing: run robot missions while streaming live data; observe acceleration and sensor changes. (1 h)

Milestones End of Day 4:
– Sensor data successfully sent to MQTT broker.
– MongoDB contains timestamped entries with team metadata.
– Students understand each stage of the data flow.

### Day 5 – Data Visualization and Analysis

Goal: Retrieve telemetry from MongoDB and visualize robot behaviour.

• 09:30–10:00 — Recap and verify data presence in MongoDB. (0.5 h)
• 10:00–11:30 — Export data using MongoDB Compass, Looker Studio, or dashboard; prepare CSV/JSON for analysis. (1.5 h)
• 11:30–12:30 — Analyze telemetry in Google Colab / Python notebook (plot acceleration vs time, speed estimates). (1 h)
• 12:30–13:00 — Lunch
• 13:00–15:00 — Mini challenge: run new robot session, collect data, and analyze metrics (e.g., average acceleration, stability). (2 h)
• 15:00–16:00 — Prepare final dashboard or plots (Matplotlib, Looker Studio, Sheets). (1 h)
• 16:00–17:00 — Team presentations and wrap-up: 3-minute demo of telemetry pipeline and insights. (1 h)

Milestones End of Day 5:
– Telemetry retrieved and visualized.
– Teams demonstrate end-to-end data pipeline and basic analytics.
– Workshop complete.

TEAM XX - ROBOT TELEMETRY CREDENTIALS

======================================

WiFi Network:

SSID: WorkshopWiFi

Password: [provided]

MQTT Broker:

Server: automaatio.cloud.shiftr.io

Port: 1883

Username: automaatio

Password: [provided]

Your Topic: teamXX

MongoDB Connection (for analysis):

URI: [provided]

Database: workshop_teamXX

Collection: sensor_data

Dashboard:

https://automaatio.cloud.shiftr.io

Code Templates

ESP32_MQTT_Mongo.ino (Connection logic for sending data to MQTT broker)

xxxx_xxxx.ino